## Slide 1
DEVICECLUSTER · PROJECT BRIEFING
Automating device classification
What the system does, where it stands, and what it needs before production use.
ENGINE
Complete
DATABASE
Complete
QUOTA DATA
1 of 8 sections
INTERFACE
Not started
Notes: Opening slide. Set expectation: this is a status briefing, ~14 minutes, and I will be direct about what is not finished.

## Slide 2
01 · WHY THIS PROJECT EXISTS
Sorting hundreds of devices, by hand
Each device must be identified by type, assigned to a process section, and grouped into a cluster before any downstream work can begin.
Today an engineer does this by hand.
It is slow, repetitive, and two engineers working the same list will not always produce the same answer.
WHAT A DEVICE LIST LOOKS LIKE
HT27PF1B
Heater
LL37PL1
Low level switch
TC37PR1
Temperature transmitter
V09CF2DA
On/off valve
Hundreds per project · sorted by hand today
Notes: Open on the problem, not the technology. If asked how long the manual sort takes today — we have not measured it. Worth getting that number.

## Slide 3
02 · WHAT WE BUILT
The tags already carry meaning
1
Identify the device — by rule
The leading letters of a tag are looked up in a reference table an engineer owns — 92 prefixes covering 23 device types. A match is certain; anything unrecognised is sent for review rather than guessed.
2
Predict section and cluster
Here we do use machine learning. Two chained models return a ranked list of candidate sections and clusters with a confidence score against each — not a single answer.
3
Fit against quota rules
A cluster can only hold so many devices of each type. That is a design constraint, so predictions are fitted to the intended composition.
Notes: If pressed on "AI": this is pattern recognition trained on our own historical projects, not a general-purpose AI. It learns our conventions specifically.

## Slide 4
03 · HOW IT WORKS
Allocation runs in three passes
FIRST PASS
Fill to quota
Each cluster takes its best-matching devices, up to its target count.
SECOND PASS
Measure the gap
Identify which clusters are still short, and by how much.
THIRD PASS
Try second choices
Unplaced devices try their next-ranked clusters, strongest device first.
THEN
Whatever is left over is not forced anywhere. It goes to a review queue for an engineer, with the model’s own suggestions attached.
Notes: The point to land: the system never silently guesses. Anything it is unsure about goes back to a person with its reasoning attached.

## Slide 5
04 · WHERE WE ARE NOW
The engine is complete and verified
Tested against a live database and the real trained models — server and local runs agree exactly.
✓
The whole pipeline is one function call
The developer building the interface does not need to understand the internals. They call one method and receive the results — from the server or locally.
✓
Nothing is hardcoded any more
Quota patterns now live in a database table an engineer can edit directly. Previously a rule change needed a developer.
Everything the system produces is written back to SQL Server — the interface reads from the database, not from files.
Notes: This is the least visible work in the project and the most important for its lifespan. It is the difference between a prototype and something maintainable.

## Slide 6
04 · WHERE IT RUNS
Deployed across two servers
1
The models run on a server
They are loaded into memory once and answer requests over the network. No engineer machine needs Python or the model files installed, and predictions are roughly ten times faster than before.
2
The database is company-shared
Everything the system produces is written to SQL Server on the company database server. The interface will read results from there, not from files passed between machines.
3
The developer builds from source
The code is in Azure DevOps. The software developer clones it and builds — nothing is emailed, and there is no package to keep re-sending each time something changes.

## Slide 7
05 · CONSTRAINTS
One number needs explaining
Chart: 
| Unclassified | No quota room | Assigned
Devices | 28 | 240 | 90
PROJECT A9998 · 358 DEVICES PROCESSED
Only 25% assigned
This is not a measure of model accuracy.
It is a measure of missing reference data. The system cannot place a device into a cluster whose target composition has never been defined — and we have defined one section out of eight.
Notes: CRITICAL DELIVERY POINT. Show the chart, then explain it immediately. If the 25% hangs unexplained for even a few seconds it reads as "the model only works a quarter of the time", which is wrong and hard to walk back.

## Slide 8
05 · CONSTRAINTS, CONTINUED
What is not ready
BLOCKER
Quota patterns are mostly placeholder
Real target numbers exist for Section 2 only. Sections 1 and 3–8 hold invented figures, added so the pipeline could be tested.
BLOCKER
No user interface yet
What we are handing over is the engine, not the finished product. The screens still have to be built.
GAP
Validated on representative, not live, data
We need a run against a completed project where the answer is already known, so accuracy is measured rather than estimated.
GAP
No automated test suite
All verification so far has been by hand. Interface work will need automated checks so nothing breaks silently.
Notes: Be direct here. Credibility comes from naming these plainly rather than being asked.

## Slide 9
06 · WHAT HAPPENS NEXT
Three things, in order of what unblocks most
01
Real quota patterns from engineering
For sections 1 and 3 through 8. The single biggest constraint on how much the system can place automatically. Needs domain knowledge, not development time.
02
Interface development
The libraries, the documentation and the deployment steps are all in source control, and a fresh clone builds cleanly. The software developer can begin immediately.
03
Validation run on a real project
This is what gives us a defensible accuracy figure — which we do not have today and should not estimate.
Notes: Item one is the ask. Make sure the room understands it does not depend on the development team.

## Slide 10
The engineering work is done, and it is solid.
What stands between us and production use is reference data and an interface — not unsolved technical problems.
The most useful thing this room can do is help us get the quota patterns for the remaining seven sections.
Notes: Close on the ask, not on the technology. Then open the floor.

## Slide 11
APPENDIX · ANTICIPATED QUESTIONS
Backup
How accurate is it?
No validated figure yet — and I will not quote one from test data. A real project run is needed.
Is any of it actually deployed?
Yes — the prediction service runs on our server as a Windows service. What is missing is the interface, not the engine.
What if it gets something wrong?
It does not silently guess. Low-confidence devices go to a review queue with ranked suggestions.
Does it replace the engineer?
No. It does the mechanical first pass and flags what it is unsure about.
If our naming convention changes?
Models need retraining. A known ongoing maintenance cost.
Will it work for another customer?
Yes — quota patterns are stored per customer, so it is configuration, not a rebuild.
Notes: Do not present this slide. Hold it for questions.