## 21.04.2026
TIMELINE WORKING PROGRESS - XENXIBLE DEVICE IDENTIFIER
NAME : | SITI SYAZIYAH BINTI SAMIRI
PROJECT : | DEVICE IDENTIFIER
TASK NAME | BUCKET | START | FINISH
> Developing Machine Learning Model (Section & Cluster)
Synchronization with DevOps | R-Medium | 2025-10-13 | 2026-06-30
Research Model Development | R-High | 2025-10-13 | 2026-04-03
Proof of concept | R-High | 2026-04-06 | 2026-04-07
Data Preparation | R-High | 2026-04-08 | 2026-04-13
Pipeline Overview | R-High | 2026-04-14 | 2026-04-15
Model Training, Testing, Evaluation | R-High | 2026-04-16 | 2026-04-24
Model Tuning & Refinement | R-High | 2026-04-27 | 2026-04-30
Model Application | R-High | 2026-05-04 | 2026-05-18
Output Post Processing | R-High | 2026-05-19 | 2026-05-22
Model Integration (Python -> C#) | R-High | 2026-05-25 | 2026-05-28
Backup Plan - Model Development | R-Low | 2026-06-01 | 2026-06-05

## 13.04.2026 (hidden)
TIMELINE WORKING PROGRESS - XENXIBLE DEVICE IDENTIFIER
NAME : | SITI SYAZIYAH BINTI SAMIRI
PROJECT : | DEVICE IDENTIFIER
MODEL DEVELOPMENT (as in 30 March 2026 - Obsolete)
PROGRESS HISTORY | OUTPUT
Develop the ML model separately | DONE
Prefix (SGD Classifier) | DONE
Suffix (XGBoost + DBScan) | DONE
NEXT PLAN | MONTH | STATUS | COMMENT
Create Dummy Structured Data | W3 APRIL | Done
Research : XGBoost Model |  | Ongoing
Data Preparation | 2026-04-13
UGS, Oiltek | 2026-04-13 | Done | complete UGS(A2020) 1 project, Oiltek (a1706) 1 project
reproduce dataset - 6 project each dataset | 2026-04-14 | Done | reproduce another 5. become 6 project each. Using dummy data
list all the possible question to ask regarding the data | 2026-04-15 | Done
complete - proof of concept | 2026-04-15 | Done
Model Development
Fit dataset on XGBoost Model | 2026-04-15 | Ongoing
Training XGBoost | 2026-04-15 | Ongoing
XGBoost result output | 2026-04-16 | Planning
XGBoost application | 2026-04-17 | Planning
2026-04-17
removal project from same source. Replace with dummy |  | Done | 1 project 5 dummy
extrapolation of XGBoost application |  | Ongoing | Stuck with the output and how they assign the prediction. Seem weird?
cross tabulate testing prediction vs testing output in training dataset |  | Stuck
2026-04-20
Backup plan about ML model |  | Planning
Fill in planner for xenible creator |  | Planning
Others
Decide approach
Develop the pipeline
Develop the coding
Develop wrap up by c++ using
Sync all the coding into DevOps
Gantt Chart | Month
1. Complete Model Development | APR
2. Synchronize all the work in git and devops | APR
3. Decide to proceed or to stop the model | MAY
4. Training course (8-10 June) | JUNE
6. Deployment ML | JULY
AUG
SEPT
OCT
NOV
DEC

## 10.04.2026 (hidden)
TIMELINE WORKING PROGRESS - XENXIBLE DEVICE IDENTIFIER
NAME : | SITI SYAZIYAH BINTI SAMIRI
PROJECT : | DEVICE IDENTIFIER
MODEL DEVELOPMENT
PROGRESS HISTORY | OUTPUT
Develop the ML model separately | DONE
Prefix (SGD Classifier) | DONE
Suffix (XGBoost + DBScan) | DONE
NEXT PLAN | MONTH | STATUS | COMMENT
Research : DBScan and Subtraction Method | W2 APRIL | Ongoing
1. develop coding using method DB scan for pattern detection | 2026-04-06 | Ongoing | ***the model is not stable (need to modify feature)
2. develop coding model (euclidean distance) |  | Ongoing
3. try on dataset - Oiltek |  | Ongoing | good with minor classification
4. dataset - Lipico |  | Stuck | major error with missed classification. Need troubleshooting
Conclusion = | 2026-04-08 | Not Yet
Decision = Proceed / Reject |  | Not Yet
Research : ML design pattern ranking | W3 APRIL | Planning
1) Source : kaggle, github, stackoverflow, reddit, dev.to
2) Execute the model (+troubleshoot)
Conclusion =
Decision = Proceed / Reject
Research : Autocorrect and word suggestion | W4 APRIL | Planning
Source : kaggle, github, stackoverflow, reddit, dev.to
Execute the model (+troubleshoot)
Conclusion =
Decision = Proceed / Reject
Others
Decide approach
Develop the pipeline
Develop the coding
Develop wrap up by c++ using
Sync all the coding into DevOps
Gantt Chart | Month
1. Complete DBSCan Unsupervised ML | APR
2. Synchronize all the work in git and devops | APR
3. Decide to proceed or to stop the model | MAY
4. Training course (8-10 June) | JUNE
6. Deployment ML | JULY
AUG
SEPT
OCT
NOV
DEC