## Project Progress
Date | Month | Progress / Activity | Details | Status
31/07/2026 | July | Draft flowchart | Stage 1 - Stage 3 | Pending on Stanley review
31/07/2026 | July | Using Dummy data for logic | Refer to the slide “Movement of dataset [UPDATE 04/08/26]” | Synch in Git
31/07/2026 | July | Cleaning README.md | Synch with devops | Synch in Git
04/08/2026 | August | Update full flowchart ML | Source: flowchart ML development.xlsx; Model development; Model application; Result of model evaluation | Synch in Git
04/08/2026 | August | Draft flowchart | Stage 1 - Stage 3; Source dataset for TRAINING MODEL; SGD Classifier: C:\Users\sitisyaziyah\Documents\Device_Identifier_MainFolder\Dataset\output\masterfile.csv; XGBoost: C:\Users\sitisyaziyah\source\repos\DeviceCluster\1.training_model\dummy_data; SGD Classifier: Wilmar, Oiltek, UGS; XGBoost: Wilmar, Oiltek, UGS (edit!!) | Synch in Git
05/08/2026 | August | Decision of 2 methods in cluster logic | Max (highest predicted cluster) choose it independently; Constraint based similarity (consider the percentage first then select the most fit one) | Synch in Git
05/08/2026 | August | Logic dll development in Visual Studio | Start: 05/08/2026. Completed: 01/09/2026 | Synch in Git
17/08/2026 | August | Build up new pipeline | EQUIPMENT TYPE = Logic function – no model involved; Script “predict_equipment.py”; Integrated inside C#; Section and Cluster = XGBoost Model; Proceed as previous model | Synch in Git
18/08/2026 | August | Handle JSON file in C# | A9998_devices.json = Name based on the project from SQL; unallocated_device_ids.json = Single file, Dedupe key and unique (DeviceId + ProjectCode), Status lifecycle; floating_deviceid.json = Used in quota allocation, contain percentage prediction of cluster, Single file | Synch in Git
18/08/2026 | August | Handle JSON file in C# | A9998_devices.json = model.dll; unallocated_device_ids.json = logic.dll; floating_deviceid.json = logic.dll | Synch in Git
19/08/2026 | August | Change dbo.DummySection2OiltekA9998 into dbo.DummyTestingData (1 project) | Complete change for all related path | Synch in Git
19/08/2026 | August | Add class function in PythonSQL [LoadProjectDataAsync] |  | Synch in Git
19/08/2026 | August | Add multiple project with many client |  | Synch in Git
19/08/2026 | August | Check json make sure unique for 1 entry | unallocated_device_ids.json; floating_deviceid.json | Synch in Git
19/08/2026 | August | Pattern hardcoded in assign cluster – GetDraftQuotas() | PROBLEM: current example only applicable for SCETION 2 only. ACTION: need to create dummy pattern for cluster quota allocation for ALL the section = by CustomerCode. TYPE FILE: SQL [dbo.PatternCluster] | Synch in Git
21/08/2026 | August | Setup the output console apps for fulfilled and vacant |  | Synch in Git
21/08/2026 | August | Sync mindmap and coding |  | Synch in Git
21/08/2026 | August | Add dbo.DeviceReviewQueue |  | Synch in Git
21/08/2026 | August | Setup output dbo in SQL – dbo.OutputDeviceAssignment |  | Synch in Git
21/08/2026 | August | Insert Output db SQL return back |  | Synch in Git
26/08/2026 | August | Question: Should I save in JSON or SQL | If inside JSON, how the UI can detect and relate; Suggestion = save in SQL so that easier to map | Synch in Git
PENDING | PENDING | Using Nuget to handover the dll library |  | PENDING
27/08/2026 | August | Draft system architecture of ML |  | Synch in Git
28/08/2026 | August | Create flowchart.md |  | Synch in Git
01/09/2026 | September | Run thru the PC server port 8000 | CMD files 1 click; "C:\Users\sitisyaziyah\source\repos\DeviceCluster\Prediction_service\DeviceClusterServiceApp\run-service-app.cmd"; exe files: "C:\Users\sitisyaziyah\source\repos\DeviceCluster\Prediction_service\DeviceClusterServiceApp\bin\Debug\net10.0-windows\win-x64\DeviceClusterServiceApp.exe" | Synch in Git
01/09/2026 | September | Server configuration | Server: 128.100.8.213; Port 80 (Azure Devops); Port 8000 (ML_SERVICE_URL); Service: http://128.100.8.213:8000; Python 3.13; ML package - scikit-learn, xgboost, pandas, numpy, scipy, joblib, fastapi, uvicorn | Synch in Git
01/09/2026 | September | Finalize DeviceIdentiferProgress.pptx | Filepath: "C:\Users\sitisyaziyah\source\repos\DeviceCluster\handoff\DeviceIdentifierProgress.pptx" | Synch in Git
01/09/2026 | September | Register the ML service as a Windows service (via NSSM) | Currently started by hand in a PowerShell window on SSSBPD01 — it stops when that window closes, when the user logs off, or when the server reboots; NSSM wraps python -m uvicorn service:app --host 0.0.0.0 --port 8000 so Windows starts it automatically at boot and restarts it if it fails | Synch in Git
02/09/2026 | September | Revise documentation | handoff\DeviceIdentifier-API-FullReference.docx; handoff\DeviceIdentifier-API-QuickReference.docx | Synch in Git
02/09/2026 | September | Revise slide presentation PPTX | handoff\DeviceCluster-Briefing.pptx; handoff\DeviceIdentifierProgress.pptx | Synch in Git
02/09/2026 | September | Entry point | DevicePipeline.RunAsync in Logic.dll | Synch in Git
02/09/2026 | September | End point | DevicePipelineResult with the assigned, unknown and unallocated devices, and writes the same results to dbo.OutputDeviceAssignment and dbo.DeviceReviewQueue. | Synch in Git
10/09/2026 | September | Change the update in Excel | Continue updating info inside Excel | Synch in Git
2026-09-21 | September | Refine "Reference\DeviceIdentifier-API-FullReference.docx" | Align with format given by Stanley at this file : "C:\Users\sitisyaziyah\Downloads\General » xenDBLink v1 2.docx" | PENDING
2026-09-21 | September | Rename dll library : Logic.dll -> XenAnalyticDevice.dll Model.dll -> XenAnalyticModel.dll Service.py -> XenAnalyticService.py | # change the readme markdown file? # DeviceIdentifier-API-FullReference.docx | PENDING
2026-09-22 | September | Update MSTeams Planner |  | PENDING